30-DAY LAUNCH CHECKLIST

From idea to first paid order in 30 days

This checklist takes you from zero to your first paid order in 30 days. Tick off each item as you complete it. Total estimated cost: ~£710 (lean start) or ~£1,600 (full kit) — see Startup Equipment workbook.

# Week 1: Legal & Registration

| # | ✓ | Task | When | Who |
| --- | --- | --- | --- | --- |
| 1 | ☐ | Check BRP card — confirm 'No restrictions' on work conditions | Day 1 | You |
| 2 | ☐ | Apply for National Insurance number if needed (gov.uk) | Day 1 | You |
| 3 | ☐ | Register as self-employed with HMRC (gov.uk/register-for-self-assessment) | Day 2 | You |
| 4 | ☐ | Register food business with Portsmouth City Council Environmental Health | Day 2 | You |
| 5 | ☐ | Buy Level 2 Food Hygiene Certificate course online (~£25) | Day 3 | You |
| 6 | ☐ | Complete food hygiene course (2-3 hours) | Day 4 | You |
| 7 | ☐ | Download HACCP food safety template pack (~£15) | Day 5 | You |
| 8 | ☐ | Apply for public liability insurance (Simply Business, ~£120/year) | Day 6 | You |

# Week 2: Banking & Accounts

| # | ✓ | Task | When | Who |
| --- | --- | --- | --- | --- |
| 9 | ☐ | Open business bank account (Starling/Monzo/Tide — all free) | Day 8 | You |
| 10 | ☐ | Set up Stripe account at stripe.com (free, instant) | Day 9 | You |
| 11 | ☐ | Sign up for FreeAgent or set up income/expense spreadsheet | Day 10 | You |
| 12 | ☐ | Buy separate business phone SIM (~£10/month) | Day 11 | You |
| 13 | ☐ | Set up business WhatsApp Business account | Day 11 | You |
| 14 | ☐ | Create folder system for receipts (digital + physical) | Day 12 | You |

# Week 3: Kitchen & Supplies

| # | ✓ | Task | When | Who |
| --- | --- | --- | --- | --- |
| 15 | ☐ | Deep clean home kitchen and create cleaning schedule log | Day 15 | Family |
| 16 | ☐ | Designate separate storage for business ingredients | Day 15 | Family |
| 17 | ☐ | Order packaging supplies (bowls, lids, cutlery, bags) — ~£80 | Day 16 | You |
| 18 | ☐ | Buy insulated delivery bags x2 (~£40) | Day 16 | You |
| 19 | ☐ | Source ingredient suppliers (cash & carry, African food shops) | Day 17 | You |
| 20 | ☐ | Buy first batch of ingredients (~£150) | Day 18 | You |
| 21 | ☐ | Test cook every menu item, refine recipes, photograph | Day 19-20 | Family |
| 22 | ☐ | Calibrate portion sizes — weigh each component | Day 21 | Family |

# Week 4: Launch

| # | ✓ | Task | When | Who |
| --- | --- | --- | --- | --- |
| 23 | ☐ | Print business cards & flyers (500 for ~£30) | Day 22 | You |
| 24 | ☐ | Test order flow on obarerebites.co.uk end-to-end | Day 23 | You |
| 25 | ☐ | Soft launch: 5 trial orders to friends/family at cost | Day 24-25 | Family |
| 26 | ☐ | Gather feedback, adjust portions, packaging, delivery | Day 26 | Family |
| 27 | ☐ | Post on Instagram & TikTok — announce opening | Day 27 | You |
| 28 | ☐ | Distribute flyers around campus & student halls | Day 28 | You |
| 29 | ☐ | Open for first paid orders — Friday evening service | Day 29 | Family |
| 30 | ☐ | Review week 1 numbers — orders, revenue, issues | Day 30 | You |

# Estimated Costs Summary

| Item | Cost |
| --- | --- |
| Food Hygiene Certificate (Level 2) | £25 |
| HACCP food safety pack | £15 |
| Public liability insurance (annual) | £120 |
| Kitchen equipment (one-off) | £200 |
| Initial ingredients stock | £150 |
| Packaging supplies (first batch) | £80 |
| Insulated delivery bags x2 | £40 |
| Business phone/SIM (3 months) | £30 |
| Business cards & flyers | £30 |
| Misc / contingency | £20 |
| TOTAL STARTUP COST (Lean / Full) | £710 / £1,600 |

Oya, let's go! Time to chop life.